2026 QUE Group Conference

San Diego, CA · September 16-18, 2026

Go-Live Checklist

Everything below should be checked off before doors open Sep 16. Nothing here is blocked on anything else in this doc -- work items in whatever order makes sense, this is a tracking list, not a sequence.

# Content

[ ]  Real 2026 Eventbrite export received and reviewed -- watch for the same issues found in the 2025 export: duplicate ticket-line rows, “Info Requested” placeholder rows, a trailing TOTALS row, and one email covering multiple attendees

[ ]  Re-run scripts/import_attendees.py against the real export -- it upserts by email, won't clobber profile fields attendees have already set

[ ]  Attendee count in the app matches expected registration count

[ ]  Any shared-email attendees flagged to Mike individually -- breaks passwordless login for the non-primary registrant on that email

[ ]  Final speaker bios and photos loaded

[ ]  Final sponsor logos and descriptions loaded

[ ]  Session schedule locked -- no more expected changes to times, rooms, or tracks

[ ]  Maps and Info pages filled in with final content -- wifi details, parking, venue info

# Testing

[ ]  Board testing pass sent and completed -- QUE-2026-Board-Testing-Email.docx

[ ]  All board-reported issues triaged; blockers fixed

[ ]  tsc --noEmit and npm run build clean on the deployed commit

[ ]  Supabase security advisory check clean -- or only the known/accepted items (admins table has no SELECT policy by design, is_admin()/current_attendee_id() intentionally callable by anon, leaked-password-protection off)

[ ]  Install + verify flow spot-checked on iOS Safari and Android Chrome

[ ]  Offline behavior spot-checked -- load a page, switch to airplane mode, confirm cached data still shows

# Comms & materials

[ ]  Attendee setup email finalized and sent -- QUE-2026-Attendee-Setup-Email.docx (sends from your own email, not the app)

[ ]  Registration table + door signage printed -- QUE-2026-Signage.docx

[ ]  QR code confirmed scannable on the printed signage -- QUE-2026-App-QR.png

# Admin & operations

[ ]  Mike's admin account confirmed working in production

[ ]  Someone assigned to watch /admin/feedback during the event

[ ]  Someone assigned to moderate Questions and Photos during the event

[ ]  Email sending confirmed end-to-end in production -- OTP verification and “Email me this list” both tested for real

[ ]  Announcement flow tested -- post a test announcement, confirm it shows up, confirm you know how to retract/correct one if needed

# Day of

[ ]  Venue wifi details double-checked in the Info page right before doors open

[ ]  Footer build version confirmed to match the latest deploy -- rules out a stale cache showing old content

[ ]  quegroup.mikecarey.tech loads cleanly from a fresh/incognito session

Living document -- add rows as things come up between now and Sep 16.